European guidelines for quality assurance in cervical screening

Guidelines Activities

15. January 03	Time schedule for each chapter

(each chapter responsible reports to Co-ordination Centre

24.-25. February 03	Workshop Munich for Chap. 6, 7

6-7. March 03	Network workshop "Guidelines", Munich

24-25. March 03	Workshop Copenhagen Chap. 2, 9, 11

30. April 03	Deadline for all chapter drafts (2, 3, ...12)

29-30. June 03	Network meeting, Helsinki

30. June 03	First draft of integrated Guidelines

21-24. Sept. 2003 	Guidelines workshop in Ormylia

Discussions of integrated chapters

1. Oct. - 20. Nov. 03 	Guidelines integration by Co-ordination Centre + UK

1. Nov. 2003 	Review of integrated Guidelines by selected external experts

20. Nov. 2003 	Release of 1st Draft of Guidelines

26. Nov. 2003  	Presentation of Guidelines at 17th International Seminar and Training Conference on Clinical Cytology in Munich

15. Dec. 03	obtain feedback via Internet from external experts

Jan-Jun 04	improve Guidelines, plan publication

June 04	send Guideline to Publication Office of European Commission

Chapter Responsibles

U. Schenck	1,  3.3,  5,  8,  10

Austria		6,  7

Belgium	3,  3.4,  3.5,  3.7

Finland	2,  9,  11

Netherlands	4

Sweden	3.2

UK		3.6,  12

Work in the Chapters

Austria		4,  5,  6,  7

Belgium	2,  3,  3.2,  3.3,  3.4,  3.5,  3.7,  4,  5,  8,  9

Finland	2,  3.5,  4,  5,  9,  11

France-S	2,  2.2.3,  2.2.4,  2.2.5,  2.4.2,  3.2,  3.4,  8,  9, 11

France-L	2,  2.1,  3.8,  9,  11

Germany-M	1,  3,  3.3,  4,  5,  6,  7, 8,  10

Germany-Z	8,  10

Greece-A	2.2.6,  2.3.1,  4.5,  4.6,  4.7,  8

Greece-O	2.2.6,  2.3.1,  4.5,  4.6,  4.7,  8

Italy		2,  2.5.1, 3.2,  4,  5,  9,  11

Netherlands	3.4,  4,  5,  7

Portugal	3.4,  3.6,  4,  5

Spain		2,  2.2.6, 4,  5,  7,  9,  11

Sweden	2,  3.2,  8,  9,  11

UK		2.2.6,  3.6,  7,  8,  9,  10,  11,  12

_____________________

Hungary	2,  7,  7-I,  9,  10

Romania	10

Slovenia	8,  10

Switzerland	3.2,  3.4,  6,  10

Table of contents

Foreword    European Commission

1. 	Introduction U. Schenck

2. 	Epidemiological guidelines for quality assurance in cervical cancer screening

2.0	Executive Summary A.Anttila

2.1 	Introduction A.Anttila

2.2	Organisation of the screening programme

2.2.1 	Evidence-based screening policy for cervical cancer E.Lynge

2.2.2	An informed decision to initiate and run screening programmes for cervical

cancer A.Anttila

2.2.3 	Integration of an organised screening programme into the health care

system M.Fender & J.-J. Baldauf

2.2.4	Defining target population and relevant health care professionals and facilities

M.Fender & J.-J. Baldauf

2.3	Implementation of the screening programme J.Patnick & E.McCoogan

2.3.1 	Invitation

2.3.2 	Screening test and further assessment J.Patnick, 	E.McCoogan & A.Anttila

2.3.3 	Severity of the screen-detected pre-cancerous lesions and stage of cancers J.Patnick, E.McCoogan & A.Anttila

2.3.4 	Treatment of screen-detected lesions and cancers A.Anttila

2.4	Information systems and registration

2.4.1 Proposed information systems for screening programmes A.B.Miller

2.4.2  Registration of the screening programme A.Anttila

2.4.3	Data collecion of opportunistic smears A.Anttila, M.Fender

2.4.4	Registration of cervical cancers A.Anttila

2.4.5	Current legal aspects of data registration in the context of organised cervical

cancer screening M.Arbyn

2.5	Monitoring and evaluation of the screening programme

2.5.1	Evaluation of the effectiveness of screening M.Hakama

2.5.2 	Monitoring G.Ronco

2.5.3	Ascertaining the programme by means of follow-up of cervical

cancers in the target population A.Anttila

2.5.4	Cost-effectiveness A.Anttila

2.6 	Bibliography from all the authors

2.7    Glossary of terms M.Hakama

3. 	Methods and Techniques of Cervical Screening  Belgium (link to 4, 5, 6)

3.0	Executive summary

3.1 	Assessment of the performance of screening tests: principles and criteria for selection

3.2	Pap test U. Schenck, Feedback: Belgium

3.3	Liquid-based cytology Belgium, Portugal, Netherlands, France-S, CH

3.4	Automation in cervical cancer screening Belgium, Finland

3.5 	HPV Sweden, Feedback: Italy, Belgium, France-S, CH

3.6	Other new technologies: Colposcopy  UK, Portugal

3.7	Comparison of Methods and Techniques Belgium , Italy ( ~ Chapter 2)

3.8 	European definition of terms France-L (ENCR, CaMon)

3.9 	Tables

3.10	Bibliography

Appendix 1:	Best practices for HPV J. Dillner

Appendix 3: 	Collection of adequate Pap smears M. Arbyn, J.-J. Baldauf, J. Jordan

Appendix 5 	Propositions for a European cytological reporting system. U. Schenck

4. 	Laboratory guidelines for cervical screening Netherlands, U. Schenck, Italy, Spain, Austria, Belgium, Finland, Portugal

4.1	Executive summary  P. Klinkhamer

4.2	Introduction  P. Klinkhamer

4.2.1	Aim   P. Klinkhamer

4.3	Personnel and organisation P. Klinkhamer

4.3.1	Final responsibility

4.3.2	Responsibilities for quality control

4.3.3	Requirements for cytotechnologists

4.3.4	Requirements for the cytopathologist

4.3.5	Administrative personnel

4.3.6	Certification and continuing education (~ Chap. 6, 10)

4.4	Material requirements   P. Klinkhamer

4.4.1	Building and rooms

4.4.2	Instruments/microscope

4.4.3	Working conditions

4.5	Laboratory procedures and protocols   P. Klinkhamer

4.5.1	Quality manual

4.5.2	Drafting new procedures

4.5.3	Auditing (~ Chap. 6)

4.6	Handling and analysis of cervical samples   P. Klinkhamer

4.6.1	Laboratory preparation

4.6.2	Assessment of the sample: stepwise screening

4.6.3	Archiving

4.7	Recording of results P. Klinkhamer

4.7.1	Laboratory management system

4.7.2	Authorisation of results

4.7.3	Laboratory response time

4.8	Communication

4.8.1	Patients* (( C. Anthony, J.-J. Baldauf, J. Jordan, General Appendix on “Communication with patients, patient rights, minorities”)

4.8.2	Other laboratories

4.8.3	Sample takers

4.8.4	Gynaecologists

4.8.5	Health authorities

from Chapter 2:

Appendix 1: Communication with patients ? (maybe general Appendix to the Guidelines)

from Chapter 3:

Appendix 4: 	Processing of cellular material in the laboratory and

microscopic interpretation of Pap smears

5. 	Quality assurance practices in screening laboratory U. Schenck, Netherlands, Italy, Spain, Austria, Belgium, Finland, Portugal

5.0	Executive Summary

5.1 	Introduction  (see 1992 Guidelines with section 7 "Quality assurance")

5.2.  	Process-oriented quality

5.2.1 Laboratory Handbook

5.2.2 Standard laboratory handbook

5.2.3 Laboratory inspection

5.3.   Screening Performance Issues

5.3.1 Methods for manual control the diagnostic result of the smear

5.3.2 Methods for automated quality assurance screening

5.3.3 Methods to guarantee optimal screening of the slides

5.3.4 Correlation of Cytology with results from other methods

5.4 	Operating procedures

5.5 	Interval cancers / other methods to detect false negative results

  - Professional requirements

  - References

6.	Certification of the screening process and staff skills Austria, U. Schenck, CH

Operational procedure, what criteria should be measurable, open call

Which approaches, how to chose, what we can offer

6.0 	Executive Summary

Introduction (European certification schemes)

6.1 	Certification of the screening process

6.1.1 	Indication for certification of the screening process

6.1.2 	General requirements for performance

6.1.3 	Process performance in screening cytology

6.1.4 	Recommendation for re-certification

6.2 	Certification of staff skills

6.2.1 	Indication for certification of staff skills

6.2.2 	General requirements for performance

6.2.3 	Standards for staff performance (low, ...., high)

6.2.4 Training and Re-certification (Portuguese, EFCS aptitude test)

6.3 	References

7.	Quality assurance guidelines for pathology in cervical screening Austria,

Spain, Hungary, UK (at final editing: interchange order of Chap. 6 & 7)

- Cervical biopsy, Endocervical curettage, Cone biopsy

7.0	Executive summary

7.1	Cervical biopsies

7.1.1	Indication (in accordance with chap. 8)

Specify types of lesion (LSIL, HSIL, carcinoma)

Suspect Colposcopy (Leucoplacia, Condyloma)

7.1.2	Diagnostic goal

Histological evaluation of suspect lesions

Resection of small lesions

7.1.3	Technique

Macroscopic description

Serial sections

7.2	Endocervical curettage

7.2.1	Indication (in accordance with chap. 8)

Suspect glandular cells in cervical smear

7.2.2	Diagnostic goal

Histological evaluation of

- endocervical neoplasms

- endometrial carcinoma involving the cervix

- remnants of CIN

7.2.3	Technique (Serial sections)

7.3	Cone biopsy

7.3.1	Indication (in accordance with chap. 8)

Diagnostic evaluation and clarification of positive cytology

7.3.2	Diagnostic goal

Diagnosis and treatment (resection) of neoplastic lesions

7.3.3	Technique

Knife conisation, Laser conisation, LEEP/LLETZ (Large Loop Excision of the Transformation Zone),

- Macroscopic description

- Adequate orientation of cone specimens to define resection margins prior to paraffin embedding

- Serial sectioning

- Immunohistochemistry to support diagnosis of microinvasion or vascular involvement

  - Quality Assessment

7.5	References

Appendix 1: European Terminology for pathology Austria, Netherlands, Hungary

8. 	Guidelines for management of women with cervical cytological abnormalities U. Schenck, Belgium,  France-S, Germany-Z, Greece-O, Greece-A, UK, Slovenia

(see 1992 Guidelines  with section 4  "Management of the patient")

  - Executive summary

  - Introduction

  - Methods for Further Diagnostic Follow Up in case of Abnormal Cytology

  - Modalities for the Treatment of Screen Detected Lesions

  - Management of Women According to Cytological abnormalities

  - Conditions for Local Destructive Therapy of Cervical Intraepithelial Neoplasia

  - Complications after Treatment of Cervical Lesions

  - Management of patients in special clinical situations

  - Quality Assurance of the Patient Management

  - Controlling the indications for further follow up

  - Glossary

  - Examples of Procedural schemes from different settings

  - References

from Chap 3: Appendix 2: Best practices for colposcopy J. Jordan, J.-J. Baldauf

9.	Data collection on treatment and follow-up of screen-detected lesions (team of chapter 2)

Finland, Belgium, Italy, Spain, France-S, France-L (ENCR), Italy
	Feedback: Sweden, (Hungary)

(see 1992 Guideline  with section 5 "Monitoring on Programme")

9.0	Executive summary

9.1	Background and aims

9.2 	Data required

9.3	Audit procedures

9.4 	References

- Guidelines for training U. Schenck, Germany-Z, Greece-O, UK,

(Hungary, Romania, Slovenia, Switzerland)

10.1 Introduction

10.2 Continuing education

-----------(see 1992 Guidelines with section 6 "Training")------------

10.9 References

11.	Summary table of key performance indicators Finland + team of chapter 2

12.	Summary table for screening programme UK + all

very important for introduction + map with red, yellow, green

benchmarks (each country, European dimension)

(see 1992 Guidelines with annex A "Monitoring").

Annexes

I 	Position paper. Recommendations on cancer screening in the European Union

II 	Recommendation R (94) 11 of the committee of ministers to Member States

on screening as a tool of preventive medicine

III	Recommendations for "European Criteria for Certification"

----------to be defined---------

VI 	Directive 95/46/EC of the European Parliament and of the Council of 24

October 1995 on the protection of individuals with regard to the

processing of personal data and on the free movement of such data

VII 	Dutch population screening act