CHAPTERS 2, 9 and 11 on monitoring, epidemiology and evaluation

Responsible. Finland  (A. Anttila)

Participants:  Finland (Dr. Anttila), Italy (Dr. Ronco, Prof. Segnan), France-Str (Dr. Fender), Belgium (Dr. Arbyn), Sweden (Prof. Dillner), Netherlands (N.N.), Spain (N.N.), Greece-O (C. Anthony), France-L (N.N.)

Associated: Slovenia (M. Zakelj), Hungary (M. Bodo)

Aim

To draft the chapters 2, 9 and 11 of the QA guideline.

Rationale for the up-date, overall goal: To provide tools for improvements in the cervical cancer screening programmes in Europe, particularly, as to the organisation and implementation of the screening policies; effectiveness; and evaluation aspects

Staff involved

The work for guideline update will consist of written contributions from some of the network members; as well as of the advisory experts in the amounts needed.

At maximum three of the advisory experts can be financially supported to take part in September to finalise and approve the first draft of the whole guideline.

We plan to involve 7 advisory external experts:

A. Miller (Germany), M. Hakama (Finland), P. Nieminen (Finland),

E. Lynge (Denmark), J. Patnick (UK), H. Vainio (WHO France-Lyon),

E. McGoogan (UK).

The members and external experts should provide necessary information, references and other background materials for the work. Literature search for some limited areas (e.g. on the differential screening policies; effect of differential age groups of screening intervals...) can be arranged. ENCR/Lyon will also be consulted.

Content

- The content of the chapter 2 "Epidemiological guidelines for quality assurance in cervical screening" will be provided.

- The content of the chapter 9 "Data collection on treatment of screen-detected lesions" will be provided.

- The content of the chapter 11 "Summary table of key performance indicators" will be provided.

- The support of other chapters of the guidelines (in form of comments and advice) will be ensured, with emphasis on how the screening programme should be organised.

Time schedule

March 2003. 	Participants of the work group consisting of the network members will meet in early March in Ormylia, to agree on the tasks within the group and discuss about the existing drafts. Meeting with the advisory experts will be arranged in Copenhagen in 24-25th March 2003. Authors and other tasks will be finally agreed in the Copenhagen meeting. Contributions of the network members as well as drafts of the tables are needed as early as possible already before the meeting in Copenhagen.

April 2003.	Drafts will be sent to A. Anttila, who will compound the first draft of the chapters required at the end of April. The first version will be shown to the co-ordination centre.

June 2003. 	The texts of the chapter 2, 9, and 11 will be presented and discussed in the network meeting arranged in Helsinki in June; and finalised by the authors shortly thereafter.

September 2003. The first draft of the Chapter 2, 9 and 11 will be improved and integrated in the whole guidelines, and released in the context of the network meeting in September 2003.